HOMEWORK 7

Project Update: Stakeholders, Charters, Risk, Communication and Cost Plan

Student Name: Muaaz Ismail

Course: Project Management

Assignment: Homework 7 (project update document and update video)

Project: Team Collaboration and Task Management Platform, a web-based platform where users log in, create or join a team, add team members, and assign and track tasks.

# 1. Project Overview

The Team Collaboration and Task Management Platform is a web application that helps a project team organize work in one place. Team members log in, collaborate with other members, assign responsibilities and monitor task progress. The goal is to improve coordination, make responsibilities clear, and reduce confusion about deadlines and task ownership.

## What This Update Adds or Changes

| Section | Update in this version |
| --- | --- |
| 2. Stakeholder analysis | New. Power–Interest Grid, engagement strategy, communication plan with meeting cadence and reporting methods. |
| 3. Team charter | New. Purpose, goals, roles, working agreements, decisions, conflict resolution, quality and tools plan. |
| 4. Project charter | New. Purpose, scope, deliverables, risks, success criteria and budget summary. |
| 5. Resource and cost plan | Updated. Bottom-up estimate shown step by step, monthly cashflow, and a RACI matrix. |
| 6. Risk management and Appendix A | Updated. 16 risks (4 per category) in a full risk register with probability, impact, owner and response. |
| 7. Quality management | New. How quality assurance and quality control are applied. |
| 8. Security incident check | New. Response to the CIS-UH GitHub security incident. |
| 9. Leadership and conflict scenario | New. API failure before release, with leadership styles and conflict techniques. |

# 2. Stakeholder Analysis: Power–Interest Grid

|  | LOW INTEREST | HIGH INTEREST |
| --- | --- | --- |
| HIGH POWER | KEEP SATISFIED Course administration; sponsor approving resources | MANAGE CLOSELY Instructor / project owner; project lead |
| LOW POWER | MONITOR Indirectly affected people; occasional observers | KEEP INFORMED End users; development team members; testers |

Stakeholder analysis identifies the people or groups who can influence the project or are affected by it. The Power–Interest Grid places each stakeholder by their power (influence over decisions and resources) and their interest (how concerned they are about the outcome). The quadrant decides how we engage them: manage closely, keep satisfied, keep informed, or monitor.Figure 1. Power–Interest Grid for the Team Collaboration and Task Management Platform.

| Quadrant | Stakeholders | Engagement strategy |
| --- | --- | --- |
| High power, high interest: Manage closely | Instructor / project owner; project lead | Share regular progress updates, involve them in key decisions, review risks and milestones, and request timely feedback. |
| High power, low interest: Keep satisfied | Course administration; any sponsor approving resources | Provide concise milestone reports, communicate major risks early, and seek approval when scope or schedule changes. |
| Low power, high interest: Keep informed | End users; development team members; testers | Share updates, demonstrate features, collect feedback, explain changes, and keep tasks and decisions visible. |
| Low power, low interest: Monitor | People indirectly affected by the platform; occasional observers | Give general updates when relevant and involve them if their needs or interest change. |

## Communication Plan

Our team has 4 members, so there are 4 × (4 − 1) / 2 = 6 possible communication paths. A fixed meeting cadence and one shared task board keep those paths manageable. Information is tailored to the audience: high-level progress and metrics for the instructor and sponsors, detailed tasks for developers.

| Meeting | Participants | Frequency | Purpose |
| --- | --- | --- | --- |
| Daily stand-up | Development team, tester | Daily (15 minutes, chat is fine) | What was done, what is next, and any blockers. |
| Weekly progress meeting | Whole team, project lead | Weekly | Deeper check of tasks, risks, budget and priorities for the next week. |
| Sprint review / demo | Team, instructor, end users and testers | Monthly and at each prototype | Show finished features, collect feedback, confirm direction. |
| Milestone update | Instructor, administration / sponsor | At each milestone or when escalation is needed | Schedule, scope, resource needs and major risks. |

| Stakeholder | Information needed | Reporting method | Frequency |
| --- | --- | --- | --- |
| Instructor / project lead | Progress, risks, decisions, deliverables | Short status report, dashboard or meeting | Weekly and at milestones |
| Development team | Tasks, priorities, blockers, technical decisions | Trello board and team meeting | At least weekly; blockers immediately |
| End users / testers | Feature changes, usability, known issues | Demo, feedback form or test session | At each prototype or release |
| Sponsor / administration | Schedule, scope, resource needs, major risks | Concise written update | At milestones or on escalation |

# 3. Team Charter

A team charter defines how the team will work together: its purpose, roles, communication practices, decision-making approach and expectations. It governs how the team operates, while the project charter (Section 4) authorizes the project itself.

## Team Purpose

To design, develop, test and present a usable team collaboration and task management platform that helps users coordinate team membership, assign work and track progress.

## Shared Goals

- Deliver a working prototype that supports the agreed core features.

- Make task ownership and progress easy to understand.

- Keep the interface clear and simple for the intended users.

- Test key user flows, record issues and fix high-priority defects.

- Complete project documentation and presentation by the agreed deadline.

## Roles and Responsibilities

| Role | Main responsibilities | Accountability |
| --- | --- | --- |
| Project Lead / Coordinator | Plan work, maintain priorities, run meetings, track risks and deadlines, prepare project documentation and the update video. | Overall progress and coordination |
| Developer 1 | Implement login and team membership features; review pull requests; maintain the repository. | Code quality and working features |
| Developer 2 | Implement task assignment and task tracking; keep screens and workflows consistent; maintain the API fallback. | Working features and usability |
| Tester / Reviewer | Test key flows, report bugs, verify fixes and check acceptance criteria. | Test coverage and issue reporting |

## Working Agreements

- Communicate respectfully and share relevant information with the team.

- Keep task status up to date and raise blockers as soon as they appear.

- Agree on priorities before starting work that affects shared components.

- Use version control and review changes before they are merged into the main branch.

- Attend planned check-ins, or tell the team in advance if unavailable.

- Document important decisions so that absent members can catch up.

## Communication and Decision-Making

The team uses a shared Trello board to track tasks, owners, deadlines and status, and follows the meeting cadence in Section 2. Routine decisions are discussed collaboratively. If a decision is time-sensitive, the project lead decides after considering the available input and explains the reasoning to the team.

## Conflict Resolution

Members first discuss disagreements directly and respectfully, focusing on project goals and evidence, and aim for collaboration and compromise. If the conflict remains unresolved, the project lead helps clarify the issue and agrees a practical next step with the team. Urgent risks affecting quality or security are escalated immediately.

## Quality Expectations

Core features are tested before demonstration. Changes must not knowingly break existing functionality. The team prioritizes security, reliability, usability and clear documentation over adding unnecessary features.

## Tools and Technology Plan

- Task board: Trello, because it is visual, easy to learn and free for our team size.

- Source control: GitHub. The main branch stays stable and deployable at all times.

- Branching: All new code is written on descriptive feature branches, and branches are deleted after merging. Nobody pushes directly to main.

- Reviews: Every change goes through a pull request with at least one teammate review before it is merged.

- Task linking: Trello cards are linked to GitHub pull requests so task status updates automatically.

- Commits: Small, logical commits with meaningful messages (for example “Fix login validation bug”, not “Changed stuff”).

- Automation: GitHub Actions to build and run tests on each pull request, so a task is only marked Done when the code works.

# 4. Project Charter

A project charter is a high-level document that authorizes and defines the project. It summarizes the purpose, objectives, scope, deliverables, stakeholders, constraints and measures of success.

| Project Title | Team Collaboration and Task Management Platform |
| --- | --- |
| Project Purpose | Provide a central web-based place for team members to coordinate, assign responsibilities and track tasks. |
| Problem / Need | Team work becomes disorganized when responsibilities, progress and communication are spread across different tools. |
| Objectives | 1) Provide secure user login. 2) Support team membership. 3) Allow tasks to be assigned to team members. 4) Show task status and progress. 5) Produce a demonstrable, tested prototype. |
| In Scope | Login and basic user access; team creation or membership; task creation and assignment; task status tracking; basic interface; testing and documentation. |
| Out of Scope | Advanced analytics, complex enterprise permissions, third-party integrations, mobile applications, and large-scale production deployment unless specifically required. |
| Key Deliverables | Working prototype; stakeholder Power–Interest analysis; team charter; project charter; risk register; communication plan; cost plan and RACI matrix; testing notes; update video. |
| Key Stakeholders | Instructor / project owner, project lead, development team, end users and testers, and any sponsor or administrator. |
| Budget | $23,870 total (labor $20,800, hosting $600, tools $300, 10% contingency $2,170). Details in Section 5. |
| Assumptions | Team members have access to development tools and can communicate regularly. The first release focuses on core functionality rather than advanced features. |
| Constraints | Limited time, available team capacity, technical dependencies and course submission requirements. |
| Major Risks | Task-assignment API failure, integration defects, feature delays, limited testing time, security incidents and cost overruns. See Section 6 and Appendix A. |
| Risk Responses | Prioritize core features, clarify requirements early, test incrementally, use version control and backups, and communicate blockers promptly. |
| Success Criteria | Users can log in, access the relevant team, assign a task, update its status and see who is responsible. Core flows pass testing and deliverables are submitted on time. |
| Approval / Authorization | Project owner and course instructor / evaluator, according to course requirements. |

# 5. Resource and Cost Plan

We used bottom-up estimation: each role’s hours are estimated, multiplied by an hourly rate, and summed. We also made a top-down check against a rough overall budget of $24,000.

## Bottom-Up Estimate

| Item | Hours / months | Rate | Calculation | Cost |
| --- | --- | --- | --- | --- |
| Project Lead (PM) | 60 h | $40/h | 60 × 40 | $2,400 |
| Developer 1 | 200 h | $40/h | 200 × 40 | $8,000 |
| Developer 2 | 200 h | $40/h | 200 × 40 | $8,000 |
| Tester | 80 h | $30/h | 80 × 30 | $2,400 |
| Labor subtotal (540 hours) | 540 h |  |  | $20,800 |
| Cloud hosting and database | 3 months | $200/month | 200 × 3 | $600 |
| Developer tools and licenses |  |  |  | $300 |
| Total before contingency |  |  |  | $21,700 |
| Contingency (10%) |  |  | 0.10 × 21,700 | $2,170 |
| Total estimated budget |  |  |  | $23,870 |

The 10% contingency covers known unknowns such as API overages and technical debt. Compared with the top-down figure of $24,000, the bottom-up total of $23,870 differs by $130 (about 0.5%), so the two methods agree.

## Monthly Cashflow (3 Months)

| Month | Labor | Infrastructure | Licenses | Contingency (10%) | Total |
| --- | --- | --- | --- | --- | --- |
| Month 1 | $8,000 | $200 | $0 | $820 | $9,020 |
| Month 2 | $8,000 | $200 | $300 | $850 | $9,350 |
| Month 3 | $4,800 | $200 | $0 | $500 | $5,500 |
| Total | $20,800 | $600 | $300 | $2,170 | $23,870 |

Hidden costs we are watching: cloud hosting growth, API rate limits and overage fees, license upgrades, and technical debt. Budget at completion (BAC) is $23,870, and we will compare planned value, earned value and actual cost at each monthly review.

## RACI Matrix

R = Responsible (does the work), A = Accountable (approves the result; exactly one per row), C = Consulted, I = Informed.

| Task | Project Lead | Developer 1 | Developer 2 | Tester |
| --- | --- | --- | --- | --- |
| Requirements and SRS | A/R | C | C | I |
| UI design | A | C | R | C |
| Login and team membership | A | R | C | I |
| Task assignment and tracking | A | C | R | I |
| Code review (pull requests) | A | R | R | C |
| Testing and bug verification | I | C | C | A/R |
| Deployment and demonstration | A | R | C | C |
| Risk register and communication plan | A/R | C | C | C |
| Documentation and update video | A/R | C | C | I |

# 6. Risk Management

A risk is an uncertain future event that could affect project objectives (a problem that already exists is an issue, not a risk). We follow four steps: identify, assess, respond and track.

- Identify: risks are grouped into four categories: technical, schedule, financial and people, with 4 risks in each.

- Assess: each risk gets a probability (1–5) and an impact (1–5). The risk matrix below turns the pair into a level: Low, Medium, High or Extreme.

- Respond: each risk gets one strategy: avoid (change the plan), mitigate (reduce probability or impact), transfer (outsource or insure), or accept (acknowledge, no action).

- Track: the project lead reviews the register at the weekly progress meeting and updates status and owners.

| Probability \ Impact | Catastrophic (5) | Major (4) | Moderate (3) | Minor (2) | Negligible (1) |
| --- | --- | --- | --- | --- | --- |
| Very High (5): over 80% | EXTREME | HIGH | HIGH | MEDIUM | LOW |
| High (4): 61–80% | EXTREME | HIGH | HIGH | MEDIUM | LOW |
| Moderate (3): 41–60% | HIGH | HIGH | MEDIUM | MEDIUM | LOW |
| Low (2): 21–40% | HIGH | MEDIUM | MEDIUM | LOW | LOW |
| Very Low (1): 0–20% | MEDIUM | MEDIUM | LOW | LOW | LOW |

Figure 2. Risk matrix (probability × impact).

## Summary

| Category | Risks | High | Medium | Low |
| --- | --- | --- | --- | --- |
| Technical | 4 | 3 | 1 | 0 |
| Schedule | 4 | 2 | 2 | 0 |
| Financial | 4 | 0 | 3 | 1 |
| People | 4 | 0 | 4 | 0 |
| Total | 16 | 5 | 10 | 1 |

Highest-priority risks: T-01 (Task-assignment API stops working shortly before the final demonstration); T-02 (Integration defects between the login, team membership and task modules); T-03 (Malicious file or dependency enters the repository or a developer machine); S-01 (Core features are delayed because tasks take longer than planned); S-03 (Too little time is left for testing before the demonstration). The full register with owners and responses is in Appendix A.

Example response: the most severe technical risk is T-01, the task-assignment API failing right before release. We mitigate it by building a mock API as a fallback and testing incrementally, as described in the scenario in Section 9.

# 7. Quality Management

Quality means meeting requirements and stakeholder expectations. We define quality standards early and apply both sides of quality management.

|  | Quality Assurance (QA): prevent defects | Quality Control (QC): detect defects |
| --- | --- | --- |
| Focus | Process | Product |
| In our project | Pull request reviews, branching rules, peer review checklist, definition of done. | Test execution of the login, team and task flows, regression tests, bug reports and re-tests. |
| Owner | Project Lead and developers | Tester |

Lesson from Knight Capital (2012): an old, unused piece of code was reactivated by a partial update, with no release testing and no rollback plan, and the company lost about $440 million in under an hour. We therefore require a staging check before any release, automated tests on each pull request, a written sign-off before the demonstration, and a rollback plan.

# 8. Security Incident Check (CIS-UH GitHub)

The instructor’s security report describes a malicious Node.js loader disguised as a font file (public/fonts/fa-solid-400.woff2) that runs automatically through a crafted tasks.json when a folder is opened in VS Code. It steals credentials and can spread through stolen GitHub tokens. Our response:

- Student check: I ran a full Windows Security scan on my machine and checked my local repositories for the fake font file and the suspicious tasks.json. I am not affected.

- Rule for the team: do not clone or pull any GitHub repository that has not been inspected first. Committing and pushing is fine.

- Before opening a new project in VS Code, check for public/fonts/fa-solid-400.woff2 (a single-line file of about 8–9 KB is malicious) and for a .vscode/tasks.json that runs on folderOpen.

- If anyone is affected: disconnect from the internet, change passwords from a clean device, revoke GitHub tokens and sessions, scan, delete the project folder, reinstall VS Code and restart.

- This is tracked as risk T-03 in the risk register.

# 9. Leadership and Conflict Scenario

Scenario: the platform’s task-assignment API stops working shortly before the final demonstration. The course evaluator expects the team to present on time, while the developers recommend delaying the release until the defect is fixed.

## Recommended Response

The team first assesses the impact and whether the problem affects data integrity, security or a core user flow. The project lead supports the developers in diagnosing the issue, communicates the risk and options to the instructor, and agrees a safe plan. If the defect risks incorrect data or makes a core feature unusable, the team does not pretend the feature works. It either fixes the issue or demonstrates a clearly identified fallback, such as the mock API from risk T-01.

## Leadership Styles in This Scenario

- Authoritative: useful if an immediate decision is needed to stop an unsafe release and assign urgent responsibilities. It is fast but can limit team input.

- Democratic: gather developer input and compare options before deciding when time allows. It builds morale but can be slow under pressure.

- Servant: remove blockers, support the developers and manage stakeholder expectations without blaming anyone.

The recommended approach is a combination: collaboration to understand the issue, servant leadership to support the team, and decisive (authoritative) leadership if a time-critical quality or security decision is needed.

## Conflict Resolution Techniques

If the instructor and developers disagree on timing, we use collaboration first (solve the problem together openly) and compromise second (for example, demonstrate the working features and show the fallback for the rest). Avoidance and competition are used only briefly and with care.

# 10. Conclusion

The Power–Interest Grid helps the team choose a communication approach for each stakeholder. The team charter sets expectations for collaboration, responsibilities, conflict resolution and quality. The project charter defines purpose, scope, deliverables, risks and success criteria. The cost plan, RACI matrix, risk register and quality practices turn those documents into concrete numbers, owners and actions. Together they keep the team aligned and make project decisions clearer.

# Appendix A. Risk Register

P = probability (1–5), I = impact (1–5), score = P × I. Level comes from the risk matrix in Section 6.

| ID | Category | Description | P | I | Score / Level | Owner | Response strategy | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T-01 | Technical | Task-assignment API stops working shortly before the final demonstration. | 3 | 5 | 15: HIGH | Developer 2 | Mitigate: build a mock API as a fallback, test incrementally, and keep a rollback plan. | Open |
| T-02 | Technical | Integration defects between the login, team membership and task modules. | 3 | 4 | 12: HIGH | Developer 1 | Mitigate: automated tests on every pull request; integrate small changes often. | Open |
| T-03 | Technical | Malicious file or dependency enters the repository or a developer machine (see the CIS-UH GitHub incident). | 2 | 5 | 10: HIGH | Project Lead | Avoid: never clone or pull a repository that has not been inspected; check for fake font files and tasks.json; run security scans. | Monitoring |
| T-04 | Technical | Hosting or database outage, or loss of project data. | 2 | 4 | 8: MEDIUM | Developer 1 | Transfer: use a managed cloud database with provider backups; also keep our own regular backups. | Open |
| S-01 | Schedule | Core features are delayed because tasks take longer than planned. | 4 | 3 | 12: HIGH | Project Lead | Mitigate: prioritize core features first, keep the backlog current, review progress weekly. | Open |
| S-02 | Schedule | Requirements are unclear or change late in the project. | 3 | 3 | 9: MEDIUM | Project Lead | Mitigate: confirm requirements with the instructor early; log changes and approve them in writing. | Open |
| S-03 | Schedule | Too little time is left for testing before the demonstration. | 4 | 4 | 16: HIGH | Tester | Mitigate: test each feature as it is finished; freeze new features before the final week. | Open |
| S-04 | Schedule | One member’s unfinished work blocks other members (dependency slips). | 3 | 3 | 9: MEDIUM | Project Lead | Mitigate: make dependencies visible on the Trello board and raise blockers immediately. | Open |
| F-01 | Financial | Cloud hosting or API usage exceeds the estimate (overage fees). | 3 | 3 | 9: MEDIUM | Developer 2 | Mitigate: set usage alerts, use free tiers during development, and draw on the 10% contingency. | Open |
| F-02 | Financial | Labor hours exceed the 540-hour estimate. | 3 | 3 | 9: MEDIUM | Project Lead | Mitigate: track hours weekly against the plan and re-plan scope if the overrun passes 10%. | Open |
| F-03 | Financial | Free tool plans (Trello, GitHub) become insufficient and a paid plan is needed. | 2 | 2 | 4: LOW | Project Lead | Accept: the $300 tools budget covers a small upgrade if it is needed. | Open |
| F-04 | Financial | Technical debt creates unplanned rework and extra cost. | 3 | 3 | 9: MEDIUM | Developer 1 | Mitigate: code reviews, small commits, and refactoring time planned in each sprint. | Open |
| PE-01 | People | A team member leaves, becomes ill or is unavailable for a long period. | 2 | 4 | 8: MEDIUM | Project Lead | Mitigate: cross-train members, document decisions, and keep tasks visible so work can be reassigned. | Open |
| PE-02 | People | Conflict over priorities or design decisions slows the team. | 3 | 3 | 9: MEDIUM | Project Lead | Mitigate: follow the team charter conflict-resolution steps; escalate quickly if unresolved. | Open |
| PE-03 | People | Skill gaps in a required technology (for example authentication or the API). | 3 | 3 | 9: MEDIUM | Developer 1 | Mitigate: pair programming, short learning tasks early, and ask the instructor for help. | Open |
| PE-04 | People | Miscommunication or missed meetings cause duplicated or forgotten work. | 2 | 3 | 6: MEDIUM | Project Lead | Mitigate: stand-ups, a written summary after each weekly meeting, and one shared task board. | Open |